Church in Conversation

Nonprofit Formation Roadmap — from decision to determination letter

DRAFT V0.1 · July 15, 2026 · Exploration with real stakes, not legal advice — attorney items flagged ◆

The structure decision is made (funding log, 2026-07-15): CiC will be an earned-revenue nonprofit — pay-for-service tiers, grants, and crowdfunding all live inside it, and access-for-all gets locked into the charter. This page is the whole path from that decision to a 501(c)(3) determination letter, so every single step can be seen before any single step is taken.

# The path, dated

| When | Milestone | Cost / gate |
| --- | --- | --- |
| Jul–Aug 2026 | Church-designated fund conversation (Ring 1 giving channel — already this week’s item). Name check: “Church in Conversation” on CO SOS database + basic trademark scan. Confirm Colorado as the state (registered agent needs a physical CO street address). | $0 Gate: giving channel open |
| Sep–Oct 2026 | Board cultivation: 3–5 candidate conversations from a composition strategy (finance, legal, academic credibility). Draft articles + bylaws lock-language skeleton. ◆ Attorney consult: lock language, IP assignment (worlds/constitution/code from Mark to the nonprofit), founder-compensation procedure. | $500–1,500 (attorney — already budgeted) Gate: 3 committed board yes’s |
| Dec 2026 – mid-Jan 2027 | File Articles of Incorporation (CO SOS, online). Get EIN (same week, free). Organizational meeting: adopt bylaws + conflict-of-interest policy, elect officers, founder-comp resolution ($0 stipend until board-approved visible line). | $50 state fee Gate: entity exists — ahead of the Q1 2027 target |
| Jan–Feb 2027 | Open bank account. Register under CO Charitable Solicitations Act (required before soliciting). File Form 1023 — full form, not EZ (see page 2) — using the Proposal Packet’s 3-year budget and narrative. | $10 CCSA + $600 IRS Gate: 1023 submitted inside 27-month retroactivity window |
| Apr 2027 | Praxis 2028 nonprofit-track application window opens — apply as a registered nonprofit carrying P2 data, validation, and testimonials. (Interest form + calendar already flagged in funding log.) | $0 Gate: the deadline that set this whole timeline |
| ~Apr–Aug 2027 | IRS determination letter expected (3–6 months typical; 80% within ~191 days). Then: direct receipting, church fund grants over its balance ◆, DAF/NCF gifts open, AWS/Google/Microsoft nonprofit credits, next-Lilly-wave positioning with seminary partner. | $0 Gate: 501(c)(3) in hand, retroactive to incorporation date |

Why December–January and not late Q1: filing the 1023 in January gives the determination its 3–6 months to land around the Praxis window and before serious Ring 2 fundraising. Retroactivity makes early incorporation nearly free — exemption applied for within 27 months of formation reaches back to the incorporation date.

# What formation actually costs

| Item | Cost | Note |
| --- | --- | --- |
| CO Articles of Incorporation | $50 | Online only, immediate |
| EIN (IRS) | $0 | Same week as filing |
| CO charitable solicitation registration | $10 + annual renewal | Before any CO soliciting |
| CO periodic report | $25/yr | From first anniversary |
| IRS Form 1023 (full) | $600 | 1023-EZ would be $275 — see page 2 for why not |
| Attorney consult ◆ | $500–1,500 | Already budgeted in the Proposal Packet |
| D&O insurance | ~$600–1,200/yr | Quote when board is seated |
| Registered agent | $0 (Mark) or ~$100–150/yr | Needs physical CO street address |
| Total — bare filings | ≈ $660–685 | State + IRS only |
| Total — full first year | ≈ $1,800–3,400 | With attorney + D&O |

# Form 1023-EZ vs. full Form 1023 — the eligibility read

The test. Form 1023-EZ ($275, typically weeks) requires attesting that projected annual gross receipts will not exceed $50,000 in each of the next three years (and did not in the past three), with total assets under $250,000. “Gross receipts” means everything combined — gifts, grants, and earned revenue.

CiC against the test. The Ministry Proposal Packet’s own midpoint planning scenario is $55.1K in Phase 1 Year 1, growing to ~$105K by Year 3; its Track A midpoint funding target is $55K. Only the minimum scenario ($18.1K → $28K) stays under the line — and a single Praxis grant ($50K unrestricted) or any Lilly-scale award crosses it instantly.

The recommendation: file the full Form 1023. Three reasons.

- Integrity. CiC cannot circulate a funding packet whose planning figure is $55K while attesting to the IRS that it projects under $50K. Trustworthy Transparency applies to government forms, not just to conversations at the Table. Filing the full form is this project’s own conviction applied to its own paperwork.

- Credibility. The full 1023’s narrative and 3-year budget become a reusable credibility artifact — funders, DAF sponsors, and grant officers sometimes ask for it. The Proposal Packet has already written most of it; the work is adaptation, not creation.

- The timeline absorbs it. The full form costs $325 more and roughly 3–5 extra months. Filed in January 2027, the determination lands ~April–August 2027 — inside the window everything else needs anyway.

What the 1023 needs from the project (mostly already exists): narrative of activities (the packet’s ministry case, adapted) · 3-year budget (the packet’s scenarios) · board names and addresses · bylaws + conflict-of-interest policy · articles with the IRS-required purpose, inurement, and dissolution clauses · compensation explanation ($0 founder stipend now; the board-approved-visible-line rule, stated plainly).

## Interim giving — what changes when

- Now → determination letter: the church-designated fund is the giving channel. It stays primary past incorporation — gifts made directly to the new corporation before determination become deductible only retroactively if approval comes; the church fund carries zero donor risk.

- At determination: direct receipting begins; the church grants over the remaining designated balance ◆; NCF/DAF gifts and nonprofit cloud credits open; exemption is retroactive to the incorporation date (1023 filed within 27 months).

## The four items that are genuinely attorney work ◆

- Lock language: access-for-all and never-gated transparency written into the articles of incorporation (hardest document to amend), with supermajority protection on mission provisions. Honest note: nothing is un-amendable — the durable lock is articles + supermajority + board composition together.

- IP assignment: the constitution, worlds, code, and methodology currently belong to Mark personally and must be formally transferred (and the $750 personal spend characterized — gift vs. reimbursable).

- Founder compensation: the visible-line rule drafted to fit the IRS rebuttable-presumption safe harbor (disinterested directors, comparability data, contemporaneous minutes).

- Church-fund wind-down: the church must hold real discretion while the fund operates; the transfer at determination should be clean.

## Three decisions this page asks of you

- Timing — incorporate December 2026–mid-January 2027 (recommended) rather than later in Q1?

- Form — full Form 1023 over 1023-EZ, for the reasons above?

- Next build — green-light the board composition strategy and 3–5-candidate cultivation list as this workstream’s next deliverable?

Sources verified 2026-07-15: Colorado SOS fee schedule and charities pages; IRS Form 1023/1023-EZ pages, instructions, and user-fee schedule; Colorado Charitable Solicitations Act (C.R.S. § 6-16-104). Full reasoning and citations: Ministry/Organization/CiC_Nonprofit_Formation_Decision_Log.md.